## Fabrilife testcase
Product Name |  | Febrilife | TC Start Date | 2024-01-02 | TC Execution Start Date | 2024-01-02 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 2024-02-02 | TC Execution End Date | 2024-02-02 |  |  |  |  | PASS | 28
Epic |  |  | Test Case Developed By | Emon Arefin Santo | Browser (tested) | Yes |  |  |  |  | FAIL | 9
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 37
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Not Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Check red asterisk beside mandatory field |  |  | Failed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
|  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.fabrilife.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
|  |  |  | Checking 'Remember Me' checkbox is not enabled by default | Should not be enabled by default | Found as per expectation | N/A | 1. Goto the URL https://www.fabrilife.com/ 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox |  |  | Passed
10 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank |  |  | Passed
11 |  |  |  | Checking User Name is case insensitive | Should accept the provided input | Found as per expectation | AbbCCdd uuXXggDD | 1. Goto the URL https://fabrilife.com/ 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
12 |  |  |  | Entering blank at first position in User name | Should not accept the provided input | Not found as per expectation | Aakk kkhhQQ | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname |  |  | Failed
13 |  |  |  | Inputing User name with special characters | Should not accept the provided input | Not found as per expectation | *&&&*()))) **###@%% | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Input space at last position of firstname and lastname |  |  | Failed
16 |  |  |  | Inputing User Name with numbers | Should not accept the provided input | Not found as per expectation | 66754455 7589699 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field |  |  | Failed
17 |  |  |  | Inputing User Name with decimal numbers | Should not accept the provided input | Not found as per expectation | 78.7568.99 87.9878.4 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field |  |  | Failed
18 |  |  |  | Inputing User name with alphanumeric characters | Should accept the provided input | Found as per expectation | John88 lizz44 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
19 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | John Austin | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
23 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | tamannasana44@gmail.com | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
24 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | hgfhghjgh@yuygh | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
25 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | tamannasana44@gmail.com | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
26 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter password and confirm password |  |  | Passed
27 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | tamannasana44@gmail.com | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter invalid combinations of characters in password and confirm password |  |  | Passed
28 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Not found as per expectation | john8888 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Failed
29 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | hhg#k88 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
30 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | hjfyvj%975 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
31 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
32 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: john@8888 Confirm password: jnn8888 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
33 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | john@8888 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Disable 'Remember Me' checkbox |  |  | Passed
34 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Not found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Enable 'Remember Me' 5. Visit the site again |  |  | Failed
|  |  |  | Sending otp for varifying mail | should be send on email | Not Found as per expectation | click resister then sending otp page shown ut otp does't send to the mail | 1. Goto the URL https://fabrilife.com/click resister then sending otp page shown ut otp does't send to the mail |  |  | Failed
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning Not successfully | Input Enter in every field | 1. Goto the URL https://fabrilife.com/ 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Failed
51 |  | Functionality Testing | Log In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
53 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://fabrilife.com/ 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email:emonarefinsanto@gmail.com Password: 123456 | 1. Goto the URL https://fabrilife.com/ 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
55 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | not found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
56 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Not Found as per expectation | N/A | 1. Goto the URL https://fabrilife.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times |  |  | Passed
|  |  | Improvement Scopes | 'Remember Me' checkbox should be selected according to user
First Name Last name is better if given
Login with google can be given
Negative test

## Sheet2
TC01